## Overview & Instructions
Oil & Gas Capital Project Controls and JV Reporting Checklist
Comprehensive evaluation matrix for mega-project scheduling, contractor progress verification, AFE tracking, and Joint Interest Billing (JIB).
Publisher: | Deview Applied Energy Systems Practice
Release Version: | 2026.1 Enterprise Release
Framework Document: | Deview_Project_Controls_JV_Checklist_v2026.xlsx
How to Use This Specification & Evaluation Workbook:
1. Open the 'Requirements & Scoring Matrix' tab to evaluate internal capability gaps or vendor RFP proposals.
2. Review each requirement statement categorized by functional operational domain.
3. Assign an Operator Priority level: 'Must Have' (M), 'Should Have' (S), or 'Nice to Have' (N).
4. Score vendor responses: 5 = Full Out-of-the-Box, 3 = Configurable Extension, 1 = Custom Development Required, 0 = Non-Compliant.
5. Document integration evidence, network diode boundaries, and sovereign residency proofs in the Notes column.
6. Summary statistics and weighted scoring calculate automatically in the summary rows.

## Requirements & Scoring
Req ID | Functional Domain | Requirement Specification Statement | Priority | Internal Score (0-5) | Vendor Compliance | Audit & Technical Evidence Notes
DOMAIN 01: WORK BREAKDOWN STRUCTURE & ENTERPRISE LEDGERS
REQ-001 | Work Breakdown Structure & Enterprise Ledgers | Primavera P6 WBS mapped directly to SAP/Oracle ERP cost centers and general ledger accounts. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-002 | Work Breakdown Structure & Enterprise Ledgers | Approved baseline budgets and schedules locked with cryptographic timestamps and change-order tracking. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-003 | Work Breakdown Structure & Enterprise Ledgers | Concession equity share modeling supporting multi-tier participating interest percentages and effective-dated partner shares. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-004 | Work Breakdown Structure & Enterprise Ledgers | Hierarchical portfolio rollup across offshore facilities, subsea tiebacks, export pipelines, and onshore terminals. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-005 | Work Breakdown Structure & Enterprise Ledgers | Multi-currency budget tracking supporting statutory national currency and international contract currencies with FX revaluation. | Must Have | 5 | Compliant | Verified against technical architecture boundary
DOMAIN 02: CONTRACTOR SUBMITTALS & PROGRESS VERIFICATION
REQ-006 | Contractor Submittals & Progress Verification | Isolated contractor web portal for daily reporting of physical craft labor, equipment hours, and material delivery. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-007 | Contractor Submittals & Progress Verification | Progress claims validated against pre-agreed rules of credit and engineering deliverable verification. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-008 | Contractor Submittals & Progress Verification | Automated generation of draft Service Entry Sheets (SES) reconciled with physical progress before ERP posting. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-009 | Contractor Submittals & Progress Verification | Secure upload of inspection records, NDT test certificates, and drone survey imagery directly to work packages. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-010 | Contractor Submittals & Progress Verification | Automated dispute flagging when contractor invoice percentages deviate from verified field milestone completion. | Must Have | 5 | Compliant | Verified against technical architecture boundary
DOMAIN 03: EARNED VALUE MANAGEMENT & PREDICTIVE ANALYTICS
REQ-011 | Earned Value Management & Predictive Analytics | Automated computation of Planned Value (PV), Earned Value (EV), and Actual Cost (AC) across all WBS levels. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-012 | Earned Value Management & Predictive Analytics | Real-time tracking of Cost Performance Index (CPI) and Schedule Performance Index (SPI) without manual spreadsheet calculation. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-013 | Earned Value Management & Predictive Analytics | Estimate at Completion (EAC) forecasting using historical productivity index trends and risk-weighted simulations. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-014 | Earned Value Management & Predictive Analytics | Executive milestone variance dashboards tracking critical-path schedule float and portfolio cash burn rates. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-015 | Earned Value Management & Predictive Analytics | Early warning alerts triggered by negative productivity variances or critical path slippage. | Must Have | 5 | Compliant | Verified against technical architecture boundary
DOMAIN 04: AFE GOVERNANCE & JV CASH CALL RECONCILIATION
REQ-016 | AFE Governance & JV Cash Call Reconciliation | Multi-tier Authorization for Expenditure (AFE) drafting, internal approval routing, and partner ballot governance. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-017 | AFE Governance & JV Cash Call Reconciliation | Automated monthly joint venture cash call generation with multi-currency reconciliation and advances management. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-018 | AFE Governance & JV Cash Call Reconciliation | Joint Interest Billing (JIB) drilldown enabling non-operating partners to inspect underlying contractor submittals. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-019 | AFE Governance & JV Cash Call Reconciliation | Real-time budget exhaustion alerts triggered when commitments plus actuals exceed 80% and 100% of approved AFE ceilings. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-020 | AFE Governance & JV Cash Call Reconciliation | Comprehensive audit trail for joint venture audit defense and partner exception resolution. | Must Have | 5 | Compliant | Verified against technical architecture boundary
DOMAIN 05: IN-COUNTRY VALUE (ICV) & LOCAL CONTENT AUDITING
REQ-021 | In-Country Value (ICV) & Local Content Auditing | Tracking contractor workforce nationalization percentages against contractually agreed quotas. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-022 | In-Country Value (ICV) & Local Content Auditing | Auditing domestic procurement invoices and local subcontracting spend against statutory thresholds. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-023 | In-Country Value (ICV) & Local Content Auditing | Automated generation of statutory local content compliance reports (UAE ICV, Saudi IKTVA, Nigeria NOGICD, Angola Angolanização). | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-024 | In-Country Value (ICV) & Local Content Auditing | Vendor qualification registry monitoring safety accreditations, commercial trade licenses, and statutory tax certificates. | Must Have | 5 | Compliant | Verified against technical architecture boundary
REQ-025 | In-Country Value (ICV) & Local Content Auditing | Subcontractor tier-2 spend traceability to ensure true local economic retention. | Must Have | 5 | Compliant | Verified against technical architecture boundary